## Sheet1
Issue #1 | Issue Description | Date Opened | Section No: or Name | Status | Reported By | Date Closed | Comments | Age
1 | Address of Parking option is not available in the SRS | 2024-02-14 |  | New | Ravi Lohar |  | Explain on why this is require | 1
2 | As Given Short parking can be opt from 1 hour so what is the maximum time for short term parking | 2024-02-14 | 12.1 | New | Ravi Lohar |  |  | 1
3 | As short term parking and long-term parking both are available from one hour so what is the difference , long term should start from 1 day | 2024-02-14 |  | New | Ravi Lohar |  | Did you check whether the parking rates are same for Day and Hourly? | 1
4 | The User is entering only the time and date and selecting type of parking he is not provinding like name , contact no. and person details | 2024-02-14 |  | New | Ravi Lohar |  |  | 1
5 | There is no maximum time limit for each parking type | 2024-02-14 |  | New | Ravi Lohar |  | Yes. There will be no limit. Even 365 Days is fine. Consider Shoter Term as 1 Days | 1
6 | Each parking type has what kind of facilities it must be shown to customer like what kind security and so on | 2024-02-14 |  | New | Ravi Lohar |  |  | 1
7 | There is no option for the vehicle type car,bike | 15/2/2024 |  | New | Aravind A |  | This is only for Cars | 0
8 | Specify if the Parking Calculator system includes a mobile application for users | 15/2/2024 |  | New | Aravind A |  | No | 0
9 | The system did n't have an option to cancel the booking | 2024-02-15 |  | New | Raisy Anto |  | There is no advance booking. You take a ticket while parking and pay while you exit. | 0
10 | There is no option to extend the time for parking. | 2024-02-15 |  | New | Sona Sunny |  | You need to pay while exiting. So extension is not required. | 0
11 | Specify whether a person can change or upadate the leaving time after booking it once | 2024-02-15 |  | New | Saniga Sugathan |  | You take a ticket while parking and pay while you exit. | 0
12 | Maximum and minimum duration for short-term,and long term parking. | 15/02/2024 |  | New | Anamika P M |  | 1 Day for Short and No Limit for Long | 0
13 | Add system security and data privacy requirements. | 15/02/2024 |  | New | Anamika P M |  |  | 0
14 | Specify error scenarios requiring unique handling. | 15/02/2024 |  | New | Anamika P M |  | Will be done during development only |  | #VALUE!
15 | Specify circumstances for lost ticket fee. | 15/02/2024 |  | New | Agna Rajesh |  | The car owner can contact customer support. The customer will have to pay 2X | 0
16 | Long term garage parking time limits | 15/02/2024 |  | New | Agna Rajesh |  | No Limits | 0
17 | The document mentions weekly discounts for specific parking options but does not provide details on any other potential discounts or promotions that the system may offer. | 2024-02-15 |  | New | Hena Biji |  | only weekly discounts | 0
18 | The system must accept the user details which includes name ,contact number or email of the user | 2024-02-15 |  | New | Raisy Anto |  | What is the question? | 0
19 | The system did n't mention about reservation booking | 2024-02-15 |  | New | Raisy Anto |  | No Booking | 0
20 | When the user modifies the leaving date and time, does the system dynamically updates the estimated parking cost. | 2024-02-15 |  | New | Sona Sunny |  | Caclulated while leaving the parking | 0
21 | Does the system display the detailed pricing structure accurately for each parking option. | 2024-02-15 |  | New | Sona Sunny
22 | The system should restrict the dynamic modification to the exit time only, preventing users from altering the entry time when updating parking details. | 2024-02-15 |  | New | Raisy Anto
23 | Is it possible for a person to change his parking option after completing the booking (for eg: changing from short term to long term) | 2024-02-15 |  | New | Saniga Sugathan
24 | It's not stated that the maximum limit of parking when the parking duration exceeds the limit | 2024-02-15 |  | New | Hena Biji
25 | Is it possible for a person to book the parking slot for another person using his own account or login credentials. | 2024-02-15 |  | New | Saniga Sugathan
26 | Include a requirement for providing feedback to users upon successful submission of parking details and payment. | 2024-02-15 |  | New | Bindu Kilari
27 | Estimation of parking cost is not updating based on user's entry and leaving time | 2024-02-15 |  | New | Arya R
28 | How Person can make payments what payments methods will be used credit card , debit card , upi | 2024-02-15 |  | New | Ravi Lohar
29 | How the system will identify the customer payment is completed or not. | 2024-02-15 |  | New | Sona Sunny
30 | If a user parks a Electric car and he can have a option to charge the car if the Charging option is available in that spot. | 2024-02-15 |  | New | Nithin Raj
31 | Add a feature to allow users to save their favorite parking spots for quick access | 2024-02-15 |  | New | Suthi R
32 | The document mentions a daily maximum rate for short-term parking, but it doesn't specify the daily rate itself. | 2024-02-15 |  | New | Hena Biji
33 | Enable users to set parking reminders to avoid exceeding parking durations | 2024-02-15 |  | New | Nithin Raj
34 | Time picker for entry and leaving time is not specified with AM/PM | 2024-02-15 |  | New | Arya R | 12.1
35 | Provide users with detailed instructions on how to reach their selected parking lot from their current location | 2024-02-15 |  | New | Nithin Raj
36 | Implement a feature for users to view live camera feeds of parking lots to access availability and security | 2024-02-15 |  | New | Suthi R
37 | Allow users to provide feedback and ratings for parking lots and their experiences. | 2024-02-15 |  | New | Sona Sunny
38 | Clarify if there are any exceptions or special considerations regarding the application of the lost ticket fee in case of valet parking. | 2024-02-15 |  | New | Hena Biji
39 | How should the system handle rounding or precision for calculated parking costs in case of cash | 2024-02-15 |  | new | Raisy Anto
40 | Add a "Contact Us" section in the app for user enquiries | 2024-02-15 |  | New | Nithin Raj
41 | Add a search feature for users to quickly find parking options | 2024-02-15 |  | New | Suthi R
42 | Ensure the system works smoothly across different devices and web browsers. | 2024-02-15 |  |  | Saniga Sugathan
43 | How does the system handle cases where users switch between daily and weekly parking options. | 2024-02-15 |  | New | Sona Sunny
44 | The system does not enforce maximum daily and hourly rates when the parking duration exceeds the corresponding limit | 2024-02-15 |  | New | Arya R
45 | How will the system ensure unauthorized access | 2024-02-15 |  | New | Jone Abutelin
46 | There is no option to track the parking location, so that customer can identify where they parked. | 2024-02-15 |  | New | Sona Sunny
47 | Is the system is able to handle a large number of users and parking transactions. | 2024-02-15 |  |  | Saniga Sugathan
48 | the system should handle situations where the parking duration exceeds the maximum limit, must notify the admin if the parking duration exceeds too long, along with adding amount | 2024-02-15 |  | new | Raisy Anto
49 | Add a search feature for users to quickly find parking option | 2024-02-15
50 | Implement alerts or notifications to remind users of expiring parking durations or upcoming reservations. | 2024-02-15 |  | New | Sona Sunny
51 | Error messages are not clear or descriptive when the customer enters invalid or inconsistent information. i.e must specify what input credential is wrong. | 2024-02-15 |  | New | Arya R
52 | Provide navigation assistance within parking lots to help users locate their reserved or preferred parking spots upon arrival. | 2024-02-15 |  | New | Sona Sunny
53 | The document specifies maximum rates for daily and hourly parking but also mentions daily maximum rates for specific parking options, which could lead to confusion. | 2024-02-15 |  | New | Saniga Sugathan
54 | The absence of information regarding handicapped-accessible parking spot availability | 2024-02-15 |  | New | Chathurya Chandran
55 | Vehicle types (two wheeler ,four wheeler,etc) and corresponding parking cost specification is missing | 2023-02-15 |  | New | Arya R
56 | Better to add Tip feature to the system. | 2024-02-15 |  | New | Bindu Kilari
57 | Allow users to change their planned departure time for parking bookings after initial confirmation. | 2024-02-15 |  | New | Chathurya Chandran
58 | It's not stated whether the system will be accessible offline. | 2024-02-15 |  | New | Jone Abutelin
59 | Lack of multi-language support for diverse customer base. | 2024-02-15 |  | New | Hena Biji
60 | Verify if users can change their planned departure time for parking bookings after initial confirmation, ensuring flexibility and convenience. | 2024-02-16 |  | New | Anjali Chandran
61 | There is no mentioning of clear refund policy in case user need to cancel their Reservation | 2024-02-15 |  | New | Anjali Chandran
Formulas:
Age = IF(ISBLANK([Date Closed]),TODAY()-[Date Opened],[Date Closed]-[Date Opened])